NCATE Executive Steering Committee

September 22, 2009

3:00pm – 4:30pm

MINUTES

Members Present:  B. Mattingly, M. Barduhn, JoEllen Bailey, John Cottone, R. Janke, S. Cohen, D. Larison, M. Goodwin, D. Farnsworth, M. Canfield, A. Berg, G. Wood, S. Cunningham

The meeting was called to order at 3:05pm by M. Barduhn.

- Accept Agenda:  The minutes were approved without modification.

- Approve Minutes:  September 8, 2009 Minutes were approved with one change:  in item  III c. change 6 departments to 3 departments.

- Old Business:

  - Task Stream Roll Out Plans Continued:  G. Wood advised the committee that Hailey Ruoff would serve as lead for the roll-out of the Task Stream training program, assisted by Amy and Gail.  A target date of October 1, 2009 has been established for the Deans of the 3 Schools to notify Gail who would be participating in the initial training initiative.

  - Sub-committee Status Reports/Action Items/Updated Membership Rosters :  Standard 1-No Report; Standard 2-Merle Canfield and Steve Cunningham indicated that the sub-committee continues to meet on a regular basis.  Merle indicated that much of the report has been completed.  The committee is having some difficulty in determining what data are being used to drive change/improvement.  Marley asked Merle to confirm membership on the committee.  He advised that currently he, Joy M. and S. Cunningham were doing the work.  Several members of the steering committee were originally assigned to the committee and will be contributing members in the future.  These individuals include G. Wood, D. Farnsworth, J. Bailey and one other member from the Childhood/Early Childhood Education Department chosen by Merle; Standard 3-R. Janke requested a meeting with Marley prior to proceeding; Standard 4-S. Cohen requested a meeting with Marley prior to proceeding; Standard 5-B. Mattingly indicated that he has a meeting of this sub-committee scheduled and will share all standard 5 presentations from the NCATE Institutional Orientation with members before the meeting takes place; Standard 6-J. Cottone indicated that he will be scheduling a meeting for his sub-committee soon and would also share materials and presentations from the recent Institutional Orientation with membership.

  - Review status of SPA Data Reports-Merle Canfield:  Merle and Steve indicated that ICC made a request for data last week.  S. Cunningham will confirm with David Dickerson  that Math is in good shape, and J. Cottone advised that a recent conversation with B. Hodges confirmed that Health was in good shape.

  - Review status of SPA Report Preparation/Readiness-Finalize the SPA Report Review Timeline/Dissemination Plan :  M. Barduhn reviewed the revised SPA Report Submission Timeline and asked for feedback from the Steering Committee.  After discussion of the timeline it was decided that the document would be forwarded to the Provost for final approval and dissemination.  M. Barduhn also reviewed the Charge to Committee for the Spa Review Committee.  Three area of discussion developed.  First, the language related to “congruence between elements and assessment” needs to be removed as the steering committee believes this to be beyond the scope of the review process.  The spelling of Lynn Couturier’s name needs to be corrected and additional appointments to the committee need to be made.  There was also some thought and discussion about calling this a ‘review’ committee.  The steering committee feels that it should be deemed an edit committee, and named appropriately.  Second, Bruce Mattingly talked about a seminar that he recently attended, conducted by Amy Henderson Harr  and  Glen Clarke on the use of Quality Circles, and suggested that it may provide a vehicle for the edit of SPA reports.  The steering committee supported this idea and a meeting will be set up to discuss this possibility.  Third, a discussion about remuneration for services rendered in the SPA edit process was discussed but it became evident that more background  work needs to be completed before a recommendation can be made.

  - Discussion- Reaccreditation Approach-Traditional vs. Transformation Initiative –September 25, 2009 informational meeting with the Provost:  No report pending the Provost’s presentation on Friday.

- New Business:

  - NCATE Orientation Report and Recommendations:  (NCATE Institutional Orientation Synopsis and Recommendations attached)  M. Barduhn reviewed the document that synopsizes our feedback and recommendations from the recent AACATE/NCATE Institutional Orientation attended by 10 representatives from Cortland.  Each section of the report was reviewed and discussed along with the corresponding recommendation(s) of the representatives.  The steering committee concurred with the findings of the report and accepted all of the recommendations except for the suggestion to provide an opportunity for faculty to attend an AACTE webinar titled:  Toward a Professional Consensus Around Dispositions, as a number of our members felt this could wait until after the current reaccreditation.  The Steering Committee agreed to have the final report sent to the Provost and unanimously endorse all recommendations.

  - Electronic Exhibits and NCATE Technology Group-HTML, OnBase, and e-learning format demos will be reviewed by faculty group on October 1, 2009 and by NCATE Executive Steering Committee on 10/6/09.  Group members are:  Marley Barduhn, Dennis Farnsworth, Hailey Ruoff, Jim Durr and Loren Leonard

The meeting was adjourned at 4:40pm.  Next meeting will take place on Tuesday, September 29, 2009 at 3pm.

SUNY CORTLAND SPA REPORT TIMELINE

Submission Deadline:  02/01/10

09/08/09:	Steering Cmte meets to decide on review process

Recommendations for SPA Review Cmte.structure and function

09/22/09:	Finalize SPA Review Cmte structure and function.

SPA Review Cmte appointed and charged.

10/01/09:	SPA Review Cmte reviewer inter-rater reliability training begins.

10/30/09	Initial draft of SPA Report due to D. Farnsworth

Review period  10/30/09 till Thanksgiving Nov. 26

Comments and dialogue with SPA preparers/departments.

11/30/09	Revision period for SPA documents:  11/30/09-1/14/10

01/15/10	Review of Revisions:  01/01/10 through 01/15/10

01/15/10	Final SPA documents due to D. Farnsworth

Submission confirmation documents prepared and submitted.

01/31/10:	Institution submits to NCATE a date preference email with preferred dates for the onsite visit.

02/01/10	SPA Submission Deadline

07/15/10	Recognition Report Due Back to the Program by 7/15/10

9/15/10	Revised reports (rejoinders) can be submitted by September 15, 2010

02/01/11	Final decision of the SPA Due Back to Programs